## Slide 1: Ergonomics Sembreak Week 4

## Slide 2: What had been discussed last week
Review the proposal
Try Human3.6M for 3D Reconstruction
If Human3.6M also doesn’t work, try other architecture for 3D reconstruction

## Slide 3: Timeline
Content | Date | Progress
Learning Basics of Deep Learning | Sep 2022 | Done
Installing Alphapose/Openpose | Sep-Oct 2022 | Done
Learning Ergonomics Basics | Oct-Nov 2022 | Done
Forming a Framework of Time Continuous Cumulative Fatigue |  | 
Preparing for Final Exam | Nov-Dec 2022 | Done
Review the Time Continuous Cumulative Fatigue Framework | Dec 2022 | 
Trying to Extract Coordinates Using Alphapose/Openpose | Dec 2022 | 
Adding on a Cumulative Fatigue Assessment using Alphapose/Openpose with Python | Jan-Mar 2023 | 
Writing a Technical Report for our Research | Mar 2023 | 

## Slide 4: Challenges of Our Framework
Paper 4: Gallagher (2017) Easy-to-use risk assessment tool for cumulative low back loading
Paper 9: (Ryu et al. 2023) Ergonomic characteristics of expert masons
CD cut-off point: 0.03
High Risk
Low Risk
Action Limit
Paper 4
Paper 9
Risk Possibility
Associated Injury Cases
CD Assessment Model
Notes: Our job is to implement the findings in paper 4 for visual based implementation, not invent a new cumulative assessment model. Therefore, if in paper 4, they have already validated the CD assessment model, we can fairly justify that their model is accurate enough at this stage. We can validate our data by comparing to the findings in Paper 9. But how can we prove the findings in paper 4 is also applicable in other cases.

## Slide 5: Challenges of Our Framework
Paper 4: Gallagher (2017) Easy-to-use risk assessment tool for cumulative low back loading
Paper 9: (Ryu et al. 2023) Ergonomic characteristics of expert masons
CD cut-off point: 0.03
High Risk
Low Risk
Action Limit
Paper 4
Paper 9
Risk Possibility
Associated Injury Cases
CD Assessment Model

## Slide 6: Challenges of Our Framework
Paper 4: Gallagher (2017) Easy-to-use risk assessment tool for cumulative low back loading
Paper 9: (Ryu et al. 2023) Ergonomic characteristics of expert masons
CD cut-off point: 0.03
High Risk
Low Risk
Action Limit
Paper 4
Paper 9
Risk Possibility
Associated Injury Cases
CD Assessment Model

## Slide 7: Challenges of Our Framework
Paper 4: Gallagher (2017) Easy-to-use risk assessment tool for cumulative low back loading
Paper 9: (Ryu et al. 2023) Ergonomic characteristics of expert masons
CD cut-off point: 0.03
High Risk
Low Risk
Action Limit
Paper 4
Paper 9
Risk Possibility
Associated Injury Cases
CD Assessment Model

## Slide 8: Revise Our Objectives
Current Papers
Cumulative Assessment
Markerless
Cumulative Assessment
Markerless
Our Paper
Cumulative Assessment
Markerless
Cumulative Assessment
Markerless
(Paper 9)
(Paper 4)
(Others)

## Slide 9: Revise Our Objectives
Current Papers
Cumulative Assessment
Markerless
Cumulative Assessment
Markerless
Our Paper
Cumulative Assessment
Markerless
Cumulative Assessment
Markerless
(Paper 9)
(Paper 4)
(Others)

## Slide 10: Revise Our Objectives
1. Compare our risk assessment to paper 9’s risk assessment (we are more accurate)
2. Compare our pose estimation to paper 9’s pose estimation (they are more accurate)
Q: People may question that the risk possibility is not general enough
A: The previous studies’ validation is enough. Because the high-risk posture and low-risk posture are consistent. In this case, the risk possibilities for the postures should also be consistent, although the participants are different people. Wherever you are, whenever you are, whoever you are, same posture should get the same risk possibility, because the risk assessment is based on the load, the horizontal distance, and the bending angle. Therefore, different individuals should not affect the final results.
Q: How long is needed for the data duration?
A: Since fatigue is cumulative, the more cycles the workers repeat, the more damage they get, so we only need to anyhow follow the exact same duration of the experiment in paper 9. Then, observe and compare the outcome.
Notes: So how we validate? As long as we get the same pose estimation as using IMUs, then the risk possibilities should also be correct.

## Slide 11: Alternatives (This is easier if can get the data)
Current Papers
Cumulative Assessment
Markerless
Cumulative Assessment
Markerless
Our Paper
Cumulative Assessment
Markerless
Cumulative Assessment
Markerless
(Paper 9)
(Paper 4)
(Others)

## Slide 12: Challenges of This Week
Revise the framework, make sure we have the consensus and moving forward on the right track
Justify whether the data is applicable
3D coordinates extraction, need to try with Human3.6M first
There is no way we can get 3D coordinates from 2D image without camera calibration. The data capture is very important, must have multiple angles of view. One view is definitely not enough

## Slide 13: Next Meeting
Rewrite the proposal
Keep trying with the 3D reconstruction
Monocular 3d reconstruction
CVPR, ECCV, ICCV top tier computer vision conference
Prepare for an one-page ppt slide for authors. Make it visualized enough, less text is better