## Slide 1: Ergonomics Semester 2 Week 11

## Slide 2: What had been discussed last week
Design an algorithm to handle stress, cumulative damage, and risk
Look for the shoulder information from 3dsspp research paper

## Slide 3: Timeline
Content | Date | Progress
Learning Basics of Deep Learning | Sep 2022 | Done
Installing Alphapose/Openpose/VideoPose3D | Sep-Oct 2022 | Done
Learning Ergonomics Basics | Oct-Nov 2022 | Done
Forming a Framework of Time Continuous Cumulative Fatigue |  | 
Preparing for Final Exam | Nov-Dec 2022 | Done
Review the Time Continuous Cumulative Fatigue Framework | Dec 2022 | Done
Trying to Extract Coordinates Using Alphapose/Openpose | Dec 2022 | 
Adding on a Cumulative Fatigue Assessment using Alphapose/Openpose with Python | Jan-Mar 2023 | 
Writing a Technical Report for our Research | Mar 2023 | 

## Slide 4: Learning How to Use OpenSim

## Slide 5: Our Method VS OpenSim
a = 10
Body weight = 600N
Repetition = 30
Load = 70N
Body weight = 600N
Repetition = 1
Load = 70N

## Slide 6: Challenges of This Week
Learning OpenSim

## Slide 7: Next Meeting
Conclude our current results
Plan for the next step (research paper, conference, etc)