## Slide 1: Ergonomics Sembreak Week 2

## Slide 2: What had been discussed last week
Reframe our research
Try using Openpose to extract coordinates

## Slide 3: Timeline
Content | Date | Progress
Learning Basics of Deep Learning | Sep 2022 | Done
Installing Alphapose/Openpose | Sep-Oct 2022 | Done
Learning Ergonomics Basics | Oct-Nov 2022 | Done
Forming a Framework of Time Continuous Cumulative Fatigue |  | 
Preparing for Final Exam | Nov-Dec 2022 | Done
Review the Time Continuous Cumulative Fatigue Framework | Dec 2022 | 
Trying to Extract Coordinates Using Alphapose/Openpose | Dec 2022 | 
Adding on a Cumulative Fatigue Assessment using Alphapose/Openpose with Python | Jan-Mar 2023 | 
Writing a Technical Report for our Research | Mar 2023 | 

## Slide 4: Reframe Research Framework due to Limited Data
Title:
Visual-Based Cumulative Ergonomics Assessment using Computer Vision with Deep Learning
Aim:
Analysing the ergonomics characteristics of expert masons from the perspective of cumulative damage assessment, compare the results to the results in paper Ergonomic Characteristics of Expert Masons JuHyeong Ryu, A.M.ASCE1; Bennett Banting2; Eihab Abdel-Rahman3; and Carl T. Haas, F.ASCE4. Justification:
This research direction is meaningful because in the last two papers, we can tell from the data that the working posture of an expert mason causes the lowest compression force and moments at the respective body parts. However, the expert may not realize that their certain postures are proper postures, therefore they cannot efficiently teach the apprentices. Hence, a scientific analysis can help us to collect proper postures and train the beginners in a more systematic way.

## Slide 5: Ergonomics Characteristics of Expert Masons
Aim: To understand the ergonomic characteristics of expert masons through biomechanical analysis of 7 common masonry activities which are risky to masons, in order to adopt their skillsets for beginner masons
Motion Capture
Biomechanical Analysis
Data Collection and Processing

## Slide 6: Motion Capture
IMC System
17 IMUs
Calibration Directed by motion capture software (Axis Neuron)
3D Coordinates

## Slide 7: Data Collection and Processing
Session 1
First Course
Standard Wall
Reinforced Wall
Constrained Space
Individual 23kg
Colab 23kg
Colab 35.2kg
1
2~6
6~7
8~10
Session 2
2~6
Standard Wall

## Slide 8: Biomechanical Analysis — 1st Session
Action Limit
~ Safety Force Limit Derived from NIOSH Lift Equation
RWL = LC x HM x VM x DM x AM x FM x CM
Symbol | Meaning
LC | Load Constant (23kg or 51lbs)
HM | Horizontal Location of the object relative to the body
VM | Vertical Location of the object relative to the floor
DM | Distance the object is moved vertically
AM | Asymmetry Angle or twisting requirement
FM | Frequency and Duration of lifting activity
CM | Coupling or quality of the workers grip on the object
https://ergo-plus.com/niosh-lifting-equation-single-task/

## Slide 9: Biomechanical Analysis — 1st Session
Lumbar Compression Force
First Course
Largest Force
Standard Wall
Constant Force
Reinforced Wall
Force
Level
Constraint Spaces
Force
Level

## Slide 10: Biomechanical Analysis — 1st Session
(a) Shoulder Moment (c) Elbow Moment (They made mistake)
Shoulder Moment
Forces
Level
Elbow Moment
Forces
Level

## Slide 11: Biomechanical Analysis — 1st Session
(b) Hip Moment (They made mistake) (d) Knee Joint Moment
Hip Moment
Constant Moment
Knee Joint Moment
Constant Moment

## Slide 12: Biomechanical Analysis — 1st Session
Completion Time
Standard Wall
Constant Duration
Reinforced Wall
Time
Level
Constraint Spaces
Time
Level

## Slide 13: Biomechanical Analysis — 2nd Session
Average Lumbar Compression Force
Individual
Force
Weight
Collaborative
Force
Weight

## Slide 14: Biomechanical Analysis — 2nd Session
Lumbar Compression Force
2~4
Force decreases
4
Lowest Force

## Slide 15: Biomechanical Analysis — 2nd Session
Shoulder Moment & Elbow Moment
Shoulder Moment
Forces
Level
Elbow Moment
Forces
Level

## Slide 16: Biomechanical Analysis — 2nd Session
Hip Moment & Knee Moment
Hip Moment
Constant Moment
Knee Joint Moment
Constant Moment

## Slide 17: Biomechanical Analysis — 2nd Session
Completion Time
Individual
Force
Weight
Collaborative (23kg)
Varies with Level
Collaborative (35.2kg)
Constant Duration
Takes Time to Synchronize Lift Techniques
*** Note that the difference between individual and collaborative for 23kg at course 4 is least

## Slide 18: Conclusion
Collaborative work is safer than individual work
The most optimal working height is the waist height (course 4)
Do not carry too heavy load even though with proper posture
Proper posture is not only safer but also more efficient

## Slide 19: Challenges of This Week
Face lots of bugs when extracting the coordinates, for example cannot implement 3d rendering and webcam

## Slide 20: Next Meeting
Keep trying using Openpose to extract the coordinates
Set up research question
Do the budget for Kinect camera
Data collection
Proposal for the author
What is the unit of the coordinates extracted in openpose