## Slide 1: Ergonomics Sembreak Week 4

## Slide 2: What had been discussed last week
Review the proposal
Try Human3.6M for 3D Reconstruction
If Human3.6M also doesn’t work, try other architecture for 3D reconstruction

## Slide 3: Timeline
Content | Date | Progress
Learning Basics of Deep Learning | Sep 2022 | Done
Installing Alphapose/Openpose | Sep-Oct 2022 | Done
Learning Ergonomics Basics | Oct-Nov 2022 | Done
Forming a Framework of Time Continuous Cumulative Fatigue |  | 
Preparing for Final Exam | Nov-Dec 2022 | Done
Review the Time Continuous Cumulative Fatigue Framework | Dec 2022 | 
Trying to Extract Coordinates Using Alphapose/Openpose | Dec 2022 | 
Adding on a Cumulative Fatigue Assessment using Alphapose/Openpose with Python | Jan-Mar 2023 | 
Writing a Technical Report for our Research | Mar 2023 | 

## Slide 4: Challenges of Our Framework
Paper 4: Gallagher (2017) Easy-to-use risk assessment tool for cumulative low back loading

## Slide 5: Challenges of This Week

## Slide 6: Next Meeting
There are two objectives of our research, emphasize the cumulative damage first, then computer vision
Emphasize how we are going to need the data from the author
The background is too wordy, make it more visualized
Think about the expected findings, compare to the findings of the reference paper
Page number must be included
Find out how long the data is, and how long (threshold) do we need to perform cumulative assessment, unless there’ll be no different between usual assessment and cumulative assessment.
Try the Human3.6M for 3D Reconstruction
If Human3.6M doesn’t work, find other architecture for 3D reconstruction
Update Data collection